## Slide 1: MANAGEMENT OF EVENT
Manajemen Perhotelan
Universitas Dian Nuswantoro
2016

## Slide 2: Invitations and Hospitality Committee
Give the Food Committee a preliminary estimate of how many people will attend.
Working with the Chair to ensure invitations to guests are done
Keep details on guest lists, where they are seated, guests of guests, special requirements
Make sure you have adequate parking, handicapped access, restrooms, and a secure place for coats (don't forget hangers).
Purchase or secure donations of first-aid kits, fire extinguishers, and cell phones. Make a list of emergency phone numbers to have on hand.
Make name tags and site maps for workers and exhibitors.
Tell the Decorations Committee how many tables will be needed.
Recruit volunteers to be greeters and runners. Assign greeters to accompany celebrity guests.
Ensure guests, keynote speakers, sponsors are greeted and managed through out the event

## Slide 3: Entertainment and Publicity Committee
Plan activities and entertainment. Arrange for any necessary stage, sound, and audiovisual equipment.
Develop a media contact list. Introduce yourself to contacts at local radio stations and newspapers and ask them to publicize your event. Radio stations may accept and broadcast public service announcements (PSA's) on your event at no cost.
Usually one person at a radio station is in charge of PSA's. For each station, find out who that person is and work with him or her to arrange free air time. Most radio stations require groups wishing to broadcast PSA's to submit proof of their nonprofit status, a script of the 30-60 second announcement, and a statement about the importance of the message. Submit this information approximately 3-4 weeks before the event.
Newspapers similarly set aside space to list community events at no charge. Find out who is in charge of these listings at your local paper and submit all necessary information to him or her.

## Slide 4: Exhibits and Information Committee
Follow up on invitations to exhibitors and verify who will attend. Send confirmation letters.
Estimate the total number of exhibitors and determine space/table requirements. Be sure to include a display table for brochures and product giveaways.
Recruit volunteers to help exhibitors unload, set up, and pack up materials.
Develop event-day instructions for all volunteers, addressing such subjects as when to arrive, where to report, and how to deal with an emergency.

## Slide 5: Food and Decorations Committee
Decide what type of decorations to use and where they will be placed.
Map out where to set up exhibits, displays, food, entertainment, and registration. Pay attention to the location of electrical outlets.
Working with your designer, make promotional signs, directional signs, and posters.
If outside of a hotel environment; If serving refreshments, arrange for all required tables, tablecloths, chairs, napkins, cups, plates, and utensils for food, and recruit and organize volunteers to prepare and serve food.
Arrange for the delivery and placement of tables, chairs, and other supplies needed for exhibits, awards, and other displays.
Recruit volunteers for setup and cleanup.
Arrange to have any unused food or drink delivered to a shelter or other facility in your area that accepts such donations.

## Slide 6: 36 to 40 Weeks Before the Event
Decide who will chair the event.
Recruit key volunteers, board members, staff and possible event contractor
Decide whether to sponsor the event with a partner (that is, another group or organization in your community that would be willing to plan and host the event with you).
Think about the possible resources and special skills that a partner would bring to your event and the type of publicity or special attention that a partner would generate.
If your group decides to have a partner, consider selecting an honorary chairperson who may -- depending on his or her position and prior experience -- be able to generate added publicity and enthusiasm for your event.

## Slide 7: 36 – 40 Weeks Before
Bring everyone together and answer the following questions:
  What are your goals? How will you measure success?
  When do you want to have your event? Will any other events conflict with your date? Do you have a rain date?
  Where will you hold your event? Is the place available? Consider seating, parking, accessibility for people with disabilities, transportation, and any permit that may be required.
  How much money will you need? How can you obtain donations? Do you need a fundraiser?

## Slide 8: 36 – 40 Weeks Continued
  Who will attend your event? How many people can you accommodate?
  How long will your event last?
  Who will serve on what committee? Typical committees include: workshops, entertainment and publicity, exhibits and information, food, decorations, and invitations and hospitality.
  Recruit volunteers for each committee and appoint committee chairpersons who have the time, energy, and commitment to do the work.
Decide if tickets will be required for admission and, if so, how much they will cost, and where and when they will be sold.

## Slide 9: 24-36 Weeks
Direct the committee to send invitations to groups or individuals who may want to attend your event. The personal invitation should include the purpose, date, time, and place of your event; who to contact for tickets
Appoint a lead person to be in charge of publicity and drawing people (such as local TV and radio station personalities) to your event. This person should work closely with any honorary chairperson your group has selected.
Meet with committee heads regularly, offer help when needed, and monitor their progress.

## Slide 10: 24 – 36 Weeks
Review website
Review speaker suggestions
Finalize sponsor package and review sponsor suggestions
Start pursuing/booking Keynote Speakers
Begin booking session speakers
Begin working with designer on conference program design
Begin working with designer on conference website

## Slide 11: 12 – 16 Weeks prior
Arrange for any required payment of contractors, such as AV, Hotel of choice, table and tent rental companies.
Arrange schwag bags
Begin selling tickets, if appropriate.

## Slide 12: One Week Before
Send a copy of your press release and an information kit to every media contact. Call to confirm coverage of your event.
Confirm all deliveries and pickups.
Give the Food Committee a final count of how many people are expected to attend.

## Slide 13: One Day Before
Pick up orders and arrange deliveries.
Test audiovisual, sound, and other equipment.
Review set up tables and decorations with hotel
Do a final review to make sure all checklist items have been completed.

## Slide 14: EVENT DAY
Complete decorations.
Ensure hotel has all tables, stage, and audiovisual equipment completed
Put first-aid kits, fire extinguishers, phones, and emergency phone numbers in locations that are readily accessible but out of the way. Tell volunteers where to find these items.
Approximately 30 minutes before your event begins, brief volunteer greeters, helpers, and runners. Answer any questions and make sure everyone is ready to go.
Thank all donors, volunteers, partners, media representatives, and celebrities.
Relax and have a great event!

## Slide 15: AFTER
Return all borrowed equipment and supplies
Deliver unused food and beverages to the local shelter or facility that agreed to accept your donation.
Send thank-you letters to all who helped make the event a success.
Take notes about what you experienced, writing down what to do differently in the future and what went especially well.
Meet with your committee chairpersons for a post event evaluation.

## Slide 16: Post Event
The best way to start evaluating your event is to reflect on your original goals.
Did you plan an event and host it?
Was it well attended?
Did your community get involved? Be sure to include an evaluation step -- such as a survey for attendees or exhibitors to complete at the end of the event -- in your overall plan.
Ask yourself what you can do better to reach your goals, to involve more people in your project, and to spread your message to a wider audience. Then, make adjustments to your activities to improve your special event.

## Slide 17: Post Event Debrief
One very good way to capture feedback while celebrating successes is to organize a post event debriefing.
Attendance should be mandatory for committee chairpersons and important operational people and optional for all other volunteers.
Make the debriefing a pleasant experience. Serve refreshments, welcome and thank everyone, and explain the process for the meeting.
All staff and volunteers will share their ideas on the positive and the negative aspects of your special event.

## Slide 18: Post Event Debrief con’t
At the start of your meeting, choose someone to write everyone's comments on a flip chart and appoint a record keeper who will take careful notes and type them later for distribution to the whole group.
Ask everyone to take a few minutes and write two lists: what the group should continue doing when planning and hosting its next special event (and why); and what it should change (and how).

## Slide 19: Post Event
Send thank you letters to chairman, presenters, speakers and sponsors
Review itemized bills from hotel and AV provider and send to Office for payment
Compile evaluation results
Create final expense budget. Submit to Steering Committee

## Slide 20: NEXT
After ten months, the big event, the committees, the cost, the evaluations
Are you going to do it again?
Implement the recommendations from the evaluations and start again!

## Slide 21: Good Luck
And remember to have fun along the way